## Change order
Change order |  |  |  | Change order #
Date
From |  |  | Customer
Company |  |  | Name
Phone |  |  | Job address
Email |  |  | Phone
License #
Original contract
Contract or estimate # |  |  | Original contract amount
Contract date |  |  | Earlier change orders
Contract before this change
The change
Description of the change
Reason
Item | Quantity | Unit | Unit price | Amount | Notes
Use a negative quantity for work taken out.
Change subtotal
Tax rate
This change
New contract total
Time
Days added
Original completion date
New completion date
How the change is paid
Work on this change starts after both signatures.
This template is not legal advice. Some states set rules for home improvement contracts, such as what a contract must say and how big a deposit can be. Check yours.
Customer |  |  | Date
Contractor |  |  | Date
Template from measuredbid.com. Free to use and change.

## Example
Change order (example) |  |  |  | Change order # | 1
Sample job on the sample house, with sample rates. Not market prices. |  |  |  | Date | Sample
From |  |  | Customer
Company | Sierra Gutter Co. |  | Name | Jordan Example
Phone | (916) 555-0100 |  | Job address | 412 Sample Ridge Ct, Roseville, CA
Email |  |  | Phone | (916) 555-0114
License #
Original contract
Contract or estimate # | 1042 |  | Original contract amount | 3726
Contract date |  |  | Earlier change orders | 0
|  |  | Contract before this change | 3726
The change
Description of the change | Rotted fascia boards were found behind run 1 when the old gutters came off. Replace and paint them before the new gutters go up. The rest of the job stays as written.
Reason | Hidden damage found
Item | Quantity | Unit | Unit price | Amount | Notes
New fascia boards, run 1 (north edge) | 30 | ft | 14 | 420
Paint the new fascia boards | 30 | ft | 4 | 120
|  |  | Change subtotal | 540
Tax rate
|  |  | This change | 540
|  |  | New contract total | 4266
Time
Days added | 1
Original completion date
New completion date
How the change is paid | Added to the final payment.
Work on this change starts after both signatures.
This template is not legal advice. Some states set rules for home improvement contracts, such as what a contract must say and how big a deposit can be. Check yours.
Customer |  |  | Date
Contractor |  |  | Date
Template from measuredbid.com. Free to use and change.